## Task Table
Task Table: Solar Panel and Battery System
Status values: Not started, Stub, In progress, Done. Project Leader (Iteration 2): Jailen Patel.
ID | Task | Menu Option | Owner | Files | Functions | Expected Deliverable | Status | Target Iteration | Notes
T1 | Load sunlight data | 1 | Advaith Nair | input_reader.h/.cpp, tasks.cpp, solar_panel.cpp | readHourlyCsv(), taskLoadSunlight(), SolarPanel::setSunlight() | Reads and checks a sunlight CSV file | In progress | 3 | Reads values and checks that the file opens; other input checks not written yet
T2 | Load demand data | 2 | Advaith Nair | input_reader.h/.cpp, tasks.cpp, load_profile.cpp | readHourlyCsv(), taskLoadDemand(), LoadProfile::setDemand() | Reads and checks a demand CSV file | Stub | 3 | Moved from Teammate 3
T3 | Set up solar panel | 3 | Advaith Nair | solar_panel.h/.cpp, tasks.cpp | setSize(), energyAt(), totalEnergy(), taskSetupPanel() | Sets panel size and efficiency, prints hourly output | In progress | 3 | Prompts and energyAt() written; hourly table and total not yet
T4 | Set up battery | 4 | Jailen Patel | battery.h/.cpp, tasks.cpp | setLimits(), charge(), discharge(), taskSetupBattery() | Sets capacity, minimum charge, and rate limit | In progress | 3 | setLimits() written; charge() and discharge() are stubs
T5 | Run 24-hour simulation | 5 | Both | energy_manager.h/.cpp, tasks.cpp | runSimulation(), checkBalance(), taskRun24Hour() | Hour-by-hour routing for one day | Stub | 3 | Written together in Phase 3
T6 | Run 7-day simulation | 6 | Both | energy_manager.h/.cpp, tasks.cpp | runSimulation(), taskRun7Day() | Same routing over 168 hours | Stub | 3 | Needs 7-day sample file (S2)
T7 | Print summary | 7 | Jailen Patel | report.h/.cpp, tasks.cpp | Report::printSummary(), taskPrintSummary() | Totals and share of demand met by solar, battery, and grid | Stub | 3 | Moved from Teammate 3
T8 | Save hourly results | 8 | Jailen Patel | report.h/.cpp, tasks.cpp | Report::writeHourlyCsv(), taskSaveResults() | Hourly output CSV that opens in Excel | Stub | 3 | Moved from Teammate 3
T9 | Compare two battery sizes | 9 | Both | energy_manager.h/.cpp, report.h/.cpp, tasks.cpp | runSimulation(), printSummary(), taskCompareBatteries() | Side-by-side summary for two capacities | Stub | 4
T10 | Run class tests | 10 | Jailen Patel | tests.cpp | taskRunTests() | At least 3 passing tests per class | Stub | 4 | Still deciding between menu option and separate test program
S1 | Menu and switch | none | Advaith Nair | main.cpp | main(), printMenu() | Menu loop with one task per option | Done | 2
S2 | Sample input files | none | Advaith Nair | data/*.csv | none | Sunny, cloudy, and 7-day input files | In progress | 3 | First sunny, cloudy, and demand files made; 7-day file not started
S3 | Task table and project plan | none | Jailen Patel | docs/EECE2140_Project_Plan.xlsx | none | Updated plan each iteration | In progress | All | First version; we expect to keep changing it
S4 | README and iteration report | none | Jailen Patel | README.md, docs/ | none | Build and run steps, iteration PDF | In progress | 2 | Moved from Teammate 3
S5 | Integration and code review | none | Advaith Nair | GitHub repository | none | One working build each iteration | In progress | All | Still learning how to review and merge with branches
S6 | GitHub Issues upkeep | none | Advaith Nair | GitHub Issues | none | Every task listed with an owner and due date | In progress | All | Moved from Teammate 3
S7 | Meeting notes | none | Jailen Patel | docs/meeting_notes.md | none | Notes from each weekly meeting | In progress | All | Moved from Teammate 3

## Status Summary
Status Summary
All counts are formulas that read the Task Table sheet.
Status | Menu Tasks (T) | All Tasks
Not started | 0 | 0
Stub | 7 | 7
In progress | 3 | 9
Done | 0 | 1
Total | 10 | 17
Percent done | 0% | 5.882%
Owner | Tasks Owned | Done | Open
Advaith Nair | 7 | 1 | 6
Jailen Patel | 7 | 0 | 7
Both | 3 | 0 | 3

## Timeline
Revised Timeline
Phase | Start | End | Days | Work | Owner | Status | Change from Iteration 1
Phase 1: Planning | 2026-10-06 | 2026-10-13 | 8 | Project plan, repository, class names and header files | All | Done | Start date approximate
Phase 2: Design and individual classes | 2026-10-14 | 2026-11-06 | 24 | System design, menu with stubs, SolarPanel, Battery, LoadProfile, input reader, first tests, sample files | Advaith: SolarPanel, input reader, LoadProfile, samples; Jailen: Battery, tests, Report stubs | In progress | Now includes system design and menu. LoadProfile and Report stubs moved here after Teammate 3 left. Dates are estimates since this is our first group project.
Phase 3: Putting it together | 2026-11-07 | 2026-11-20 | 14 | EnergyManager routing, Report class, energy balance and battery limit tests, first full 24-hour run | Both | Not started | Report class now owned by Jailen
Buffer and rework | 2026-11-21 | 2026-11-29 | 9 | Bug fixes, catch-up, Thanksgiving break (Nov 26) | Both | Not started | No change
Phase 4: Finishing | 2026-11-30 | 2026-12-08 | 9 | 7-day run, battery size comparison, invalid input tests, final README, report, charts, presentation | Both | Not started | No change
Milestone: Final presentation and demo | 2026-12-08 | 2026-12-08 | 1 | Tuesday, December 8, 10:18 A.M. | Both | Not started

## Contributions
Member Contributions
Iteration | Team Member | Role | Completed This Iteration | Responsibilities Next Iteration
1 | Advaith Nair | Repository and integration | Proposed the hourly simulation idea and energy routing order; created the GitHub repository; wrote the SolarPanel and LoadProfile header files; found example solar and demand data; set up GitHub Issues; drafted the scope and tools sections | Write the SolarPanel class; write the input file reader; write the LoadProfile class; create sample input files; review Jailen's code
1 | Jailen Patel | Testing and documentation | Looked up typical home battery values; wrote the Battery and Report header files; proposed the team objectives and testing approach; drafted the objectives section; drafted the timeline and meeting notes; put together the PDF | Write the Battery class; start the test program; write the next iteration document; review Advaith's code
2 | Advaith Nair | Repository and integration | Built the menu and switch statement; wrote the stub for every task; started the CSV reader (T1) and the SolarPanel class (T3); made the first sample input files; drafted the class and file structure design; kept GitHub Issues up to date | Finish the CSV reader and its input checks (T1, T2); finish the SolarPanel and LoadProfile classes (T3); create the 7-day sample file; start EnergyManager with Jailen (T5, T6, T9); review Jailen's code
2 | Jailen Patel | Project Leader, testing, documentation | Served as Project Leader for the first time; started the Battery class (T4); wrote the Report class interface (T7, T8); made the first version of the task table and this plan; drew the class diagram; put together the Iteration 2 report; kept the meeting notes | Finish charge() and discharge() (T4); decide on a testing approach and write the first tests (T10); start the Report class (T7, T8); start EnergyManager with Advaith (T5, T6, T9); update the README and meeting notes; review Advaith's code